## Risk log
Skills/Workshops Risk Assessment
Project name: Green Week Bird Box drop in
Project manager: M Hunt
ID | Risk description | Person/s likely to be affected | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Risk Severity following mitigating action Rating based on impact & likelihood. | Contingent action Action to be taken if the risk happens.
1 | Widespread COVID Infection | Staff and workshop attendees | Medium | High | High | Emma | Rebuild staff to take LFTs ahead of event and stay at home if positive. Designtated Rebuild staff as Covid Lead to ensure all processes and procedures are followed. Hand Sanitiser to be provided on stall, workshop leader briefed to encourage social distancing and safe working practices, drop in workshop to minimise contact, sign in list instigated, encourage face masks and provide spare if needed, workshop outside so well ventilated, tools to be sanitised between use, workshop designed to be complete in less than 15 minutes | Medium | Staff to keep contact list in line with GDPR rules to contact workshop members if we are made aware of COVID outbreak arising from workshop
2 | Splinters, flying debris cause eye / face injury | Workshop attendees | Medium | High | High | Gary | Provide safety goggles and briefing to workshop members prior to activity taking place. Restrict workshop numbers to ensure adequate supervision by staff members. Ensure materials are splinter free ahead of workshop, all children and vulnerable adultsto be supervised by responsible adult/caregiver. Provide flat adequate flat surfaces are available for workshop activity | low | Refer to A+E or first aiders
3 | Bruising caused by hammers | Workshop attendees | Medium | Medium | Medium | Gary | Adequate safety briefing to participants ahead of starting and supervision during workshop. Restrict workshop numbers. Provide small hammers to minimise injury, all children and vulnerable adultsto be supervised by responsible adult/caregiver | low | Refer to A+E or first aiders
4 | Ingestion of small parts | Young childrenand vulnerable adults attending workshop | low | high | High | Gary | packs collated in advance to avoid excess small parts in workshop, all children and vulnerable adults to be supervised by responsible adult/caregiver workshop safety breifing and supervision at all times | low | Refer to A+E or first aiders
5 | Slips trips and falls | staff, stand visitors and workshop attendees | low | low | Low | Maisie | Stall to be kept tidy with all materials out of reach of public and staff members. Designated H+S lead to ensure space is kept tidy and trip hazards and slip hazards are minimised | low | Refer to A+E or first aiders if appropriate
6 | Adverse weather conditions | All | Medium | low | Medium | Maisie | Decision to call off workshop and/or stall if severe weather causes conditions to become hazardous to be kept in review | low | Pack away materials and stall

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low